## Sheet1
Task | Assignee | Estimated Time to Complete | Story Points | Actual Time to Complete
Create Admin page for database | Tom | 2hrs | 1 | 1.5hr
Working on API calls | Andrew | 3hrs | 2 | 6hrs
Create signup page | Tom | 2hrs | 1 | 1hr
Create signin page | Samuel | 2hrs | 1 | 1hr
Create account page | Xander | 2hrs | 1 | 2hrs
Update documentation | Samuel | 2hrs | 1
Create Public Listings page | Xander | 2hrs | 1 | 1.5hr
Total Remaining Story Points |  |  | 8
Date | Points Remaining
2022-03-03 | 8
2022-03-15 | 4
2022-03-17 | 1