## Sheet1
Task | Assignee | Estimated Time to Complete | Story Points | Actual Time to Complete
Setup Django Database |  | 1hr | 1
Create Models |  | 1hr | 1
Create Web page for database |  | 1.5hrs | 1
Create login and sign up pages |  | 3hrs | 1
Create HTML template for login page |  | 1hr | 1
Create HTML template for sign up page |  | 1hr | 1
Create views for login, sign up, and update urls.py |  | .5hrs | 1
Create CSS styling for site |  | 3hrs | 2
Total Remaining Story Points |  |  | 9
Date | Points Remaining
2022-02-15 | 9
2022-02-17 | 9
2022-02-22 | 9
2022-02-24 | 0
2/29/22 | 0