## Sheet1
Task | Assignee | Estimated Time to Complete | Story Points | Actual Time to Complete
Create Direct Transfer Page | Tom | 1hr | 1 | 1
Create My Listings Page | Xander/ Andrew | 1hr | 1 | 1
Create History Page | Tom | 1hr | 1 | 1
Create Public Listings Page | Xander/ Andrew | 1hr | 1 | 1
Update Documentation | Sam | 1hr | 1 | 1
Worker Reviews | Sam/ Andrew | 1hr | 1 | 1
See Workers | Sam/ Andrew | 1hr | 1 | 1
Total Remaining Story Points |  |  | 7
Date | Points Remaining
2022-03-17 | 7
2022-03-22 | 7
2022-03-24 | 7
2022-03-29 | 2
2022-03-31 | 0